## Backlog
ID | As a < type of user > | I want to < perform some task > | so that I can < achieve some goal > | MoSCoW | Priority | Story Points | Sprint | Status |  | Velocity
1 | Technician | register to the system | start using the system | Must | High | 5 | 1 | Completed | Sprint 1 | 22
2 | Technician | log in to the system | access the request list | Must | High | 5 | 1 | Completed | Sprint 2 | 28
3 | Client | register to the system | start using the system | Must | High | 2 | 1 | Completed | Sprint 3 | 24
4 | Client | log in to the system | view and sign requests | Must | High | 2 | 1 | Completed | Sprint 4 | 30
5 | Supervisor | register to the system | start using the system | Must | High | 2 | 1 | Completed
6 | Supervisor | log in to the system | send a request | Must | High | 2 | 1 | Completed
7 | Admin | register to the system | start using the system | Must | High | 2 | 1 | Completed
8 | Admin | log in to the system | access the request list | Must | High | 2 | 1 | Completed
9 | Technician/Admin | see the list of requests waiting in a queue | pick up the request | Must | High | 3 | 2 | Completed
10 | Supervisor | view the request that needs my approval | can sign it | Must | High | 2 | 2 | Completed
11 | Supervisor | sign the request | send it to the technician | Must | High | 2 | 2 | Completed
12 | Client | create a new request | ask for help | Must | High | 2 | 2 | Completed
13 | Client | fill in details of the request | send it to my supervisor | Must | High | 5 | 2 | Completed
14 | Client | send a request to my supervisor | get the approval from him | Must | High | 2 | 2 | Completed
15 | Client | select a type of my request | make it easy to filter it later | Should | High | 1 | 2 | Completed
16 | Client | select a priority level | outline how urgent my request is | Should | Medium | 2 | 2 | Completed
17 | Client/Supervisor/Technician | review request | see the details | Must | High | 5 | 2 | Completed
18 | Technician/Admin | pick request up | start working on it | Must | High | 2 | 2 | Completed
19 | Technician/Admin | add anticipated time of completion | inform my client with a timescale | Could | Medium | 2 | 2 | Completed
20 | Client | see anticipated time to complete the request | plan my time and other tasks related to this problem accordingly | Could | Medium | 2 | 3 | Completed
21 | Supervisor | track the status of requests | understand at what stage the request is at the moment | Shoud | High | 2 | 3 | Completed
22 | Client | track the status of my request | understand at what stage the request is at the moment | Should | High | 2 | 3 | Completed
23 | Technician/Admin | change the request status | inform a client about my progress | Must | High | 3 | 3 | Completed
24 | Technician/Admin | form a list of materials and their prices | see all materials ordered and a total cost | Should | High | 5 | 3 | Completed
25 | Client | view material cost table | see what materials were used and a total price of the request | Should | High | 2 | 3 | Completed
27 | Technician/Admin | access solved archived requests | find information that I need | Should | Low | 5 | 3 | Completed
28 | Client | access my archived requests | refer to them | Should | Low | 3 | 3 | Completed
29 | Technician/Admin | add comments on my request | inform about my progress | Could | Medium | 5 | 4 | Completed
32 | Technician/Admin | filter the list of requests | see realted requests | Should | Medium | 3 | 4 | Completed
33 | Admin | add new technician | get a generated code | Should | Low | 3 | 4 | Completed
34 | Admin | oversee other tecchnicians' profiles | manage my workers | Should | Low | 3 | 4 | Completed
35 | Technician/Admin | view my profile | see my details | Should | Low | 5 | 4 | Completed
36 | Technician/Admin | edit my details | update my personal information | Should | Low | 3 | 4 | Completed
37 | Supervisor | view my profile | see my details | Should | Low | 2 | 4 | Completed
38 | Supervisor | edit my details | update my personal information | Should | Low | 2 | 4 | Completed
39 | Client | view my profile | see my details | Should | Low | 2 | 4 | Completed
40 | Client | edit my details | update my personal information | Should | Low | 2 | 4 | Completed
31 | Technician/Admin | search the list of requests | find a needed one quickly | Could | Low | 5 | future | Not started
44 | Supervisor | receive notifications when my approved request gets updated | check its status | Could | Low | 5 | future | Not started
45 | Client | receive notifications when my request gets updated | check its status | Could | Low | 5 | future | Not started
30 | Supervisor | edit details of the request | fix mistakes or update it | Should | Low | 3 | future | Not started
41 | Technician/Admin | download drawing file | examine it closely | Should | Low | 3 | N/A | Not started
42 | Supervisor | attach a file of drawing | update the request | Should | Low | 5 | N/A | Not started
43 | Client | attach a file of drawing | explain the nature of the request more in depth | Should | Low | 2 | N/A | Not started
26 | Technician/Admin | enter collection time | inform client with collection dates | Could | Medium | 3 | useless | Not started

## Sprint 1
SPRINT 1
Technician | register to the system | start using the system | Must | High | 5 | Completed
Technician | log in to the system | access the request list | Must | High | 5 | Completed
Client | register to the system | start using the system | Must | High | 2 | Completed
Client | log in to the system | view and sign requests | Must | High | 2 | Completed
Supervisor | register to the system | start using the system | Must | High | 2 | Completed
Supervisor | log in to the system | send a request | Must | High | 2 | Completed
Admin | register to the system | start using the system | Must | High | 2 | Completed
Admin | log in to the system | access the request list | Must | High | 2 | Completed

## Sprint 2
SPRINT 2
Client, supervisor, technician | see home page | acess requests | Must | High | 3 | Completed
Client | create a new request | ask for help | Must | High | 2 | Completed
Client | fill in details of the request | send it to my supervisor | Must | High | 5 | Completed
Client | send a request to my supervisor | get the approval from him | Must | High | 2 | Completed
Client | select a type of my request | make it easy to filter it later | Should | High | 1 | Completed
Client | select a priority level | outline how urgent my request is | Should | Medium | 2 | Completed
Supervisor | view the request that needs my approval | can sign it | Must | High | 2 | Completed
Supervisor | sign the request | send it to the technician | Must | High | 2 | Completed
Client/Supervisor/Technician | review request | see the details | Must | High | 5 | Completed
Technician/Admin | see the list of requests waiting in a queue | pick up the request | Must | High | 3 | Completed
Technician/Admin | pick request up | start working on it | Must | High | 2 | Completed
Technician/Admin | add anticipated time of completion | inform my client with a timescale | Could | Medium | 2 | Completed

## Sprint 3
SPRINT 3
Supervisor | track the status of requests | understand at what stage the request is at the moment | Shoud | High | 5 | Completed
Client | track the status of my request | understand at what stage the request is at the moment | Should | High | 2 | Completed
Technician/Admin | change the request details - status, estimated time, technician etc. | inform a client about my progress | Must | High | 3 | Completed
Technician/Admin | view my tasks | see my progress | Must | High | 3 | Completed
Client | see estimated completion time | plan my time and other tasks related to this problem accordingly | Could | Medium | 2 | Completed
Technician/Admin | access solved archived requests | find information that I need | Should | Low | 3 | Completed
Client/supervisor | access archived requests | refer to them | Should | Low | 3 | Completed
Technician/Admin | form a list of materials and their prices | see a total request cost | Should | Medium | 8 | Completed
Client | view material cost table | see how much my request costs | Should | Medium | 2 | Completed
Client, supervisor | attach link to onedrive |  | Must | High | 2 | Completed
Technician/Admin | visit link to onedrive |  | Must | High | 2 | Completed

## Sprint 4
SPRINT 4
Technician/Admin | view my profile | see my details | Should | Low | 5 | Completed
Technician/Admin | change password | update my password | Should | Low | 3 | Completed
Supervisor | view my profile | see my details | Should | Low | 2 | Completed
Supervisor | change password | update my password | Should | Low | 2 | Completed
Client | view my profile | see my details | Should | Low | 2 | Completed
Client | change password | update my password | Should | Low | 2 | Completed
Admin | add new technician | get a generated code | Should | Low | 3 | Completed
Admin | oversee other technicians' profiles | manage my workers | Should | Low | 3 | Completed
Technician/Admin | filter the list of requests | see realted requests | Should | Medium | 3 | Completed
Technician/Admin | add comments on my request | inform about my progress | Could | Medium | 5 | Completed
Supervisor | edit details of the request | fix mistakes or update it | Should | Low | 3 | Not started
Technician/Admin | sorting the list of requests | get queeu accroding to the date | Could | Low | 5 | Completed

## TODO
Todo: | Status:
Forgot password | done
Delete account | done
Delete waiting to join person | done
Delete request | done
Update list of requests page | done
Update review request page | done
Add pagination | done
Responsiveness | done
Admin rights | done
Hosting | done
Custom search | done
Fix rules
Error page | done
From feedback:
Update custom search with a better RTA | TBD
Testing